## Instructions
Monthly Closing Project Plan: Instructions
This template outlines a sample financial closing process for a nonprofit organization. Columns A and B number and list typical steps in a financial close. Column C lists suggested staff responsibilities for each activity. "Staff" refers to front-line fiscal office staff (e.g. bookkeeper, staff accountant). "Senior Staff" refers to senior fiscal office personnel (e.g. senior accountant, controller, director of finance, CFO). Note that the assignments listed here are general in nature and should be used only as guidelines; these may be adjusted according to the structure of your organization's finance function. You may overwrite each cell with the title of the position or name of the individual responsible for each task in your own organization. Column D notes whether performing an activity is dependent on the completion of a prior activity. If so, the number of the activity that must be completed first will appear in this cell. To use the template as a project plan or Gantt chart, place an "x" in the appropriate cell in Columns E through X to identify the target completion date of each activity. Be aware of any tasks that depend on the prior completion of another activity.

## Closing Process
Activity/Task |  | Staff Responsible | Prior Activities | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Notes
Asset Account Analysis and Revenue Recognition Activities
Cash Accounts
1.1 | Print cash receipts summary reports after final day's receipts are recorded | Staff
1.2 | Close cash receipts and post to General Ledger (GL) | Senior Staff | 1.1
1.3 | Complete bank reconciliations for each cash account | Staff | 1.2
1.4 | Review and approve bank reconciliations; ensure all reconciling items have been researched and properly resolved | Senior Staff | 1.3
Accounts Receivable
2.1 | Prepare vouchers or invoices based on personnel and OTPS expenses allocated to government grants/contracts or restricted funds | Staff
2.2 | Generate A/R Aging report | Staff
2.3 | Review A/R Aging report and determine strategy for collection or write-off of aging A/R | Senior Staff | 2.2
2.4 | Post pledges receivable to GL and reconcile to balances per development department | Staff
2.5 | Reconcile to revenue reports from the development department and update GL | Senior Staff | 1.2
Prepaid Expenses
3.1 | Establish pre-paid expenses (e.g., insurance, interest expense, etc.) to recognize expense in proper month | Senior Staff
Fixed Assets
4.1 | Review new purchases made in the previous month to verify they have been recorded properly with the correct depreciation schedule | Senior Staff
4.2 | Review disposals of fixed assets and remove from fixed asset records | Senior Staff
4.3 | Record depreciation expense for the current month | Senior Staff
Investments
5.1 | Post interest and dividend income to GL | Senior Staff
5.2 | Reconcile any investment activities for the period | Senior Staff
Other Assets
6.1 | Ensure any other asset accounts are current and reconcile as necessary | Senior Staff
Accounts Payable / Liability Account Analysis
Payroll
7.1 | Post payroll to GL | Senior Staff
Accounts Payable (other than payroll)
8.1 | Submit all employee expense reports (Including original backup documentation) and vendor invoices to finance | Program Staff
8.2 | Review credit card statements and other reimbursement expense reports; match to supporting documentation for approved travel and other reimbursement expenses; verify coding | Staff | 8.1
8.3 | Close A/P and post to GL | Staff | 8.2
8.4 | Review A/P and other payables for possible accrual | Senior Staff | 8.3
Notes Payable
9.1 | As applicable, analyze notes payable accounts (e.g., notes payable for mortgages or lines of credit) and post any unrecorded interest and principal outstanding; reconcile to statements received from source(s) of financing | Senior Staff
Other Liabilities
10.1 | Ensure any other liability accounts are current and reconcile as necessary | Senior Staff
Reporting
Financial Reporting Activities
11.1 | Run preliminary budget-to-actual expense reports by department, program, and contract | Staff | all of the above
11.2 | Review and analyze month-end financial data; record adjustments as necessary | Senior Staff | 11.1
11.3 | Generate full final financial package and complete month-end financial statements for executive team and board | Senior Staff | 11.2
11.4 | Distribute appropriate reports to executive team, board, and program and development managers | Senior Staff | 11.3
11.5 | Meet with appropriate management levels to discuss variances and projections | Senior Staff | 11.4
QUARTERLY Close Activities
The following activities should be part of the closing process for the months ending a quarter, and should be completed prior to the issuance of that month/quarter's financial statements.
Q.1 | Review open purchase orders and uninvoiced services rendered to establish accruals or encumberances against budget | Staff
Q.2 | Reconcile 941 quarterly tax filings to GL | Staff | 7.1
Q.3 | Review 941 quarterly tax filing reconciliations | Senior Staff | Q.2
Q.4 | Analyze net asset accounts to ensure net assets are properly classified as unrestricted, temporarily restricted or permanently restricted, including releasing any restrictions that have been satisfied | Senior Staff
Q.5 | (After issuance of financial statements)Conduct quarterly financial review incorporating senior leadership from finance, development and program | Senior Staff | 11.4
Please Note: This document is made available by Fiscal Management Associates, LLC (FMA), for informational purposes only and does not constitute financial or professional advice. The information provided in this document is of a general nature and does not take into account your individual objectives, financial situation or needs. It should not be used, relied upon or treated as a substitute for specific professional advice. FMA recommends that you obtain your own independent professional advice before making any decision in relation to your particular requirements or circumstances. FMA does not warrant the accuracy, completeness or currency of the information provided on and made available through this document. By viewing or using this document, you acknowledge and agree that any reliance upon or use of any information made available through this document shall be entirely at your own risk. FMA shall not be liable for any loss or damage, whether direct or indirect, and however caused, to any person or organization arising from the use of (or reliance upon) information provided on and made available through this document.
© Fiscal Management Associates, LLC, 2012. All rights reserved.